## Update Template Version Project Methodology Overview for Rollout Roadmap

### Definition

The subject area “Upgrade Template Project” groups topics together that are related to the process of identifying, specifying, prioritizing, modifying and controlling updates to the Global Template This is expected to occur when:

- Unpredicted circumstances prevent template installation

- Repairs to the template are required

- Local teams identify enhancements which can significantly affect the template’s ease of use

- Other local issues arise that call for template modification

### Purpose

- Since the template has a direct relationship to the business case, changes to the template need to be carefully controlled. An effective change control framework considers the impact of template changes from the standpoint of associated up-stream and down-stream tasks and work products.

#### Project Management Overview Table

| Phase | Work Package or Activity Group | Activities | Tools or Key Accelerators | Roles | Deliverables |
| --- | --- | --- | --- | --- | --- |
| - 1 | - Initial Project Planning | - Create Project Charter | - Industry Solution Maps with KPIs, - Sample Project Charters | - Project Sponsor, TeamSAP, Project Manager, Customer, Project Manager | - Project Charter |
|  |  | - Review and Refine Implementation Strategy | - Enterprise Area Scope Document Template | - TeamSAP/ Customer Project Manager | - Enterprise Area Scope Document |
|  |  | - Establish Project Team Working Environment | - Project Room Requirements White Paper | - TeamSAP/ Customer Project Manager | - Project Room Plan, List of office equipment needed to set up project room |
|  | - Determine Project Organization | - Finalize the Project Organization for the Implementation | - Project Organization Template | - TeamSAP/ Customer Project Manager | - Organizational Diagram of Project Organization |
|  | - Prepare Project Plan | - Prepare detailed plans to monitor the progress of the project | - Microsoft Project Plan | - TeamSAP/ Customer Project Manager | - Work Plan, Budget Plan and Resource Plan |
|  | - Project Procedures | - Define Project Management and Implementation Standards and Procedures | - Issue Database | - TeamSAP/ Customer Project Manager | - Process Description for Scope and Issue Management |
|  | - Project Kick-Off | - Company wide kick-off of the project and internal project kick-off | - Project Kick-Off Agenda Template | - TeamSAP/ Customer Project Manager - Project Sponsor |  |
| - 2 | - Business Process Definition | - Setting up workshops to determine the business processes effected by the implementation and any discrepancies from the original project scope | - Q&Adb, Application Consultants Guide | - TeamSAP/ Customer Project Manager - Application Consultants | - Business Blueprint, Change Requests, Revised Budget and Project Plan, Revised Project Organization Plan |
| - 3 | - Initial planning for production support and cutover | - Determine Production Support and Cutover Plan for the time before and after going live | - Help Desk White Paper, Cutover Process Checklist, Cutover Plan Template, Cutover Process Task Schedule | - TeamSAP/ Customer Project Manager | - Production Support Plan, Cutover Plan |
|  | - Prepare Final Integration Test | - Set up a test plan for the final integration, allocate resources, ensure that test cases are established | - CATT, test scenarios (Knowledge Corner), test scenario templates, Testing strategy white paper | - TeamSAP/ Customer Project Manager - Business Process Team Lead | - Final Integration Test Plan |
| - 4 | - Detailed Project Planning | - Review the Cutover Plan based on the information available at that stage |  | - TeamSAP/ Customer Project Manager | - Reviewed Cutover Plan |
| - 5 | - Validate Live Business Process Results | - Compare achieved results with business and project measurements as established in Phase 1 of the project | - Project Charter | - TeamSAP/ Customer Project Manager - Steercom | - Project Sign Off |

## Initial Project Planning

### Definition

- Initial project planning includes the development of a project charter – the clarification of the scope of the project. It also includes establishing the project room.

### Purpose

- The main purpose of Initial Project Planning is to ensure that all parties involved have the same understanding of the project objectives, targets and scope.

### How to

- To create the project charter, interviews with the Steering Committee members must be conducted to collect their input regarding business objectives, drivers, and measurements and to consolidate them into one document. The scope of the project as well as the project milestones should have been defined in the Pre-Sales Phase and it is now important to confirm this information or to adjust them based on new parameters.

- To set up the project room, a lot of information about the project team has to be made available. Depending on the number of sites, project members, and so on, a room and the equipment inside can be planned.

## Determine Project Organization

### Definition

- The project organization includes the Steering Committee members, the project sponsor, the project managers, and the members of the different teams

### Purpose

- The purpose of this work package is to determine who will fulfill different roles during the implementation and to inform those members about their duties, the expected deliverables, and the time necessary to fulfill their tasks.

### How to

- Based on the information available in ASAP, the necessary roles for this implementation must be identified and the necessary resources must be allocated. Regarding the resources, past experience has tried different approaches and SAP can only recommend one approach here – the best people achieve the best results.

## Prepare Project Plan

### Definition

- The Project Plan includes tools and/or templates to monitor the budget, the time frame, the resources, and their deliverables.

### Purpose

- The main purpose of the Project Plan is to monitor the progress of the project in the different aspects of time and quality.

### How to

- Based on the original project plan (typically the MS Project plan as suggested by ASAP), a more detailed plan to monitor the budget, the resources, and work packages must be established. There are many different ways to develop tools and templates and most probably every Project Manager will have his own style. Also customers might want to use their own way to monitor projects.

## Project Procedures

### Definition

- Project Procedures include standards for scope and issue management, documentation, and other procedures that have to be defined at the beginning of a project.

### Purpose

- The main purpose here is make sure that all key players in the project follow the same standards and procedures to be able to monitor the progress of the project.

### How to

- Firstly, the project managers have to decide on the standards and procedures. ASAP provides quite a few tools and accelerators, for example, the Issue Database, to support this process. After finalizing the concept a meeting with all project members should be organized to communicate and agree on this concept.

## Project Kick-Off

### Definition

- All parties not only involved, but also affected by the project, have to be informed about the objectives, time frame, and players in the implementation

### Purpose

- The main purpose here is to make everyone who will be affected by the implementation aware of the project, the main business drivers behind it, and the project measurements and members.

### How to

- If possible, all members of an organization should be invited to attend the project kick-off. It is important that the Project Sponsor, or another member of the Steering Committee, take a leading role during the kick-off to show the commitment of the top players of the organization. A proposed agenda for such a kick-off can be found in the Implementation Assistant.

- It is of utmost importance that the kick-off is not the last event where staff members hear about the SAP System before going live. Instead a concept should be established as to how to inform the entire organization about the progress of the project throughout the project. Other activities to involve the organization should be considered to eventually lift the awareness level to a buying-in and ideally to a level of ownership.

## Business Process Definition

### Definition

- Business Process Definition includes the definition of all the relevant business processes of the customer, gathering of general as well as detailed information about his requirements to be able to deliver the Business Blueprint

### Purpose

- The purpose of this work package is to define the company requirements based on SAP business processes, to provide the required functions. You must first define your organizational structure.

- The business process definitions create your Business Blueprint

### How to

- To be able to compile the Business Blueprint, several workshops need to be conducted:

- During the first workshop the standardization aims (general settings) must be analyzed.

- Examples of candidates for standardization include:

- Numbering systems

- Charts of accounts

- Statistics

- Units and measurement

- Balance sheets and profitability analyses

- Handling of procedures, rules and standards for data transfer between application systems

- In the second step, the requirements for the following areas must be determined:

- Business process

- Reporting

- Interface

- Conversion

- Enhancements

- Authorization

- Since all the results gathered during the workshops subsequently create the Business Blueprint, the business process workshops are crucial. It is necessary to use the questions in the Q&Adb to determine business requirements and to complete a customer input template for each business process.

- Finally, you need to identify detailed requirements related to business processes and review deficient areas. When you conduct the detailed requirements workshop, you need to consider the following topics:

- Review identified deficient areas

- Clarify requirements using demonstrations

- Last but not least, all these activities lead to the completion of the Business Blueprint, which is the main deliverable of Phase 2. The Business Blueprint serves as your conceptual master plan, and becomes a detailed written document. This document shows you the business requirements in detail, and serves as the basis for organization, configuration and, if necessary, development activities.

## Initial Project Planning for Production Support and Cutover

### Definition

- A plan must be established for the period when the productive system is prepared to go live. You also need to establish a plan for the subsequent phase.

### Purpose

- The purpose is to ensure a smooth cutover to the productive system. This includes all activities related to the data transfer. It also includes developing a plan to ensure that sufficient support available for the system and the end users after going live.

### How to

- For the cutover, you need to prepare a plan for migrating the system and organization to a production system.

- The cutover plan focuses on the activities, tasks, and timing of the final days of effort. The main benefit is a plan to ensure a smooth transition to production. Referring to this plan if difficulties arise can serve as a guide to action. The cutover plan includes a checklist that reviews points of readiness, and provides the basis for approval to progress.

- For the phase after going live, the technical configuration for the productive system has to be finalized and the necessary hardware and software must be procured.

- To ensure sufficient support when going live, you need to establish a production support team (for short-term support after going live), a Help Desk (long term), and procedures and standards for disaster recovery in case of a system crash.

## Prepare Final Integration Test

### Definition

- Setting up a Final Integration Test Plan includes test scenarios, defined roles and responsibilities, and a time schedule.

### Purpose

- The purpose of this activity is to setup test team and logistics for the final integration test and to determine the test plan that includes:

- Test scope

- Test scenarios

- Test processes

- Timeframes for testing

- People responsible for testing

- The scope of the test is based on the process design for the enterprise areas as defined in the Business Blueprint. The goal of the final integration test is to simulate live business processing.

### How to

- Final integration testing is a critical task in your implementation. Your test plan must include the following processes and components:

- Business process

- Output

- Reports

- Interfaces

- Conversions

- Enhancements

- Technical setup (Printer, fax)

- Authorization

The final integration test plan ensures quality, and that everything defined in the Business Blueprint is tested. Identify the necessary processes and associated dependencies. Create a timeline outlining tests according to their sequence and dependencies.

This procedure describes how you prepare the integration test plan. Integration testing encompasses areas that cross departmental boundaries, bringing together the efforts of previous tasks. The objective is to build on what has already been developed.

The final integration test is process-oriented. The responsible business process owners conduct this test. It is useful to involve the extended team members in this test. Even though the extended team members may be new to the project and require some initial SAP system training, they provide two benefits: fresh outlook and closer knowledge of the business processes.

## Detailed Project Planning

### Definition

Review of the Cutover Plan as established earlier

### Purpose

The purpose of this activity is to ensure that new information, such as delays in the delivery of documents, resources not available, and so on, are incorporated into the Cutover Plan prepared earlier in the project.

## Validate Live Business Results

### Definition

Compare achieved results with business and project measurements as defined in Phase 1

### Purpose

The purpose of this activity is to ensure that the objectives defined at the beginning of the project were fulfilled and document them.

### How to

Compare the planned time frame and the agreed budget with the actual figures. Since some time may be required until the system is stable and fully working, it may be difficult to see the results of the business measurements immediately after going live.